## Wx
PROJECT REPORT
Group | <Team 1>
Week | <16/5/2022-22/5/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Requirements | Completed | Shop bán giày
2 | Create group on Github | Completed
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Font-end + Back-end | DucLM
2 | Font-end + Back-end | HungNM
3 | Font-end + Back-end | ThachDP
4 | Font-end + Back-end | HoangNV
5 | Font-end + Back-end | VoNVA
6 | Requirements - Docs | All Member
7 | Create group on Github | ThachDP
III. Project Issues
Date | Project Issue | Status | Notes (Solution, Suggestion, etc.)
17/05 | không nhận Boostrap 5 | Completed | sai link boostrap cdn
18/05 | Debug nhưng lỗi không thể hiển thị | In Progress | Debug theo từng bước
19/05 | Lỗi connect với DB | Completed | Thêm đường dẫn jstl trong file jsp
20/05 | Không insert được acc vào database | Completed | Xóa table acc tạo lại | Quy tắc làm việc nhóm: +, Tất cả mọi người phải code trung bình mỗi tuần phải code được 1 màn hình/1 người +, Teach leader kiểm tra mọi người tạo ra cấu trúc thư mục theo hướng dẫn của thầy +, Một ngày các thành viên dành ra 2h để code và 15-30m để làm tài liệu và 10-15m để họp nhóm +, Cả nhóm phấn đấu code 40-45 screen, 20-25 database table. Nguyên tắc để làm đi từ gốc của Mindmap và tên đề tài -> Tên nhóm chức năng(FeatureName) -> ScreenName -> SceenFlow -> Vẽ Mockup màn hình -> Vẽ Data table diagram -> Vẽ packege diagram Thực chất chỗ này là định hình tên của object class sẽ được sắp xếp vào các folder của project. Detail Design mô tả cấu trúc bên trong của class và mối quan hệ giữa các class = cách sử dụng Class Diagram. Mô tả giữa các class gọi nhau như thế nào thông qua Sequece Diagram +, Hằng ngày record meeting phải viết lại issue mà nhó m gặp phải (3-5 issue) và các solution
21/05 | Không merge được các nhánh trong github | In Progress | https://www.youtube.com/watch?v=lZTaQu0lNdI
21/05 | Không push được lên github | Completed | tạo 1 clone file mới
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
| Hoàn thiện IT2 | 29/5/2022 | Before 00:00 30/5/2022
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
| https://github.com/ashwinmenon/onlineShopping | ashwinmenon
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C21: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue