## Wx
PROJECT REPORT
Group | <Team 1>
Week | <16/5/2022-22/5/2022>
I. Status Report
# | Project Work Item | Status | Notes (Work Item in Details)
1 | Requirements | Completed | Shop bán giày
2 | Create group on Github | Completed
In Progress
II. Team Contribution
# | Project Task | Member | Notes (Task Details, etc.)
1 | Font-end + Back-end | DucLM
2 | Font-end + Back-end | HungNM
3 | Font-end + Back-end | ThachDP
4 | Font-end + Back-end | HoangNV
5 | Font-end + Back-end | VoNVA
6 | Requirements - Docs | All Member
7 | Create group on Github | ThachDP
III. Project Issues
Date | Project Issue | Status | Notes (Solution, Suggestion, etc.)
17/05 | không nhận Boostrap 5 | Completed | sai link boostrap cdn
18/05 | Debug nhưng lỗi không thể hiển thị | In Progress | Debug theo từng bước
19/05 | Lỗi connect với DB | Completed | Thêm đường dẫn jstl trong file jsp
20/05 | Không insert được acc vào database | Completed | Xóa table acc tạo lại
21/05 | Không merge được các nhánh trong github | In Progress | https://www.youtube.com/watch?v=lZTaQu0lNdI
21/05 | Không push được lên github | Completed | tạo 1 clone file mới
IV. Next Week Plan
# | Project Work Item | Deadline | Notes (Task Details, etc.)
| Hoàn thiện IT2 | 29/5/2022 | Before 00:00 30/5/2022
V. Other Project Masters/Suggestions
# | Project Matter/Suggestions | Raised By | Notes
| https://github.com/ashwinmenon/onlineShopping | ashwinmenon
Note on C5: Author: Pending: just planned, have not started implementing yet In Progress: planned and doing, but have not completed yet Completed: planned and completed
Note on C21: Author: Pending: issue occurred, no solution yet In Progress: occurred and handling issue Completed: occurred and handled issue